## Summary
IT Asset Management — Test Case Suite
Application | IT Transformation Hub (ithub-uat.niytri.com)
Scope | IT Asset Management module + Central Identity (Ashika Portal SSO) & RBAC
Build / Release | Release 2026-10 — contracts/AMC, warranty, depreciation, license compliance, asset dashboard, central identity
Automated run | 2026-10-18 · local UAT replica with mock Ashika Portal (SSO endpoints per Integration Guide v1.1)
Prepared by | NIYTRI Technologies
Module | Sub-module | Total cases | Automated Pass | Automated Fail | Manual (UAT) | UAT Pass | UAT Fail | UAT Pending
IT Asset Management | Asset Registry | 13 | 8 | 0 | 5 | 0 | 0 | 13
IT Asset Management | Asset Register Upload | 3 | 2 | 0 | 1 | 0 | 0 | 3
IT Asset Management | Handovers | 8 | 6 | 0 | 2 | 0 | 0 | 8
IT Asset Management | Lifecycle | 4 | 4 | 0 | 0 | 0 | 0 | 4
IT Asset Management | My Assets | 1 | 1 | 0 | 0 | 0 | 0 | 1
IT Asset Management | Employee Mapping | 9 | 9 | 0 | 0 | 0 | 0 | 9
IT Asset Management | Bulk Assignment | 2 | 2 | 0 | 0 | 0 | 0 | 2
IT Asset Management | Physical Audit | 5 | 4 | 0 | 1 | 0 | 0 | 5
IT Asset Management | Contracts & AMC | 7 | 5 | 0 | 2 | 0 | 0 | 7
IT Asset Management | Depreciation | 9 | 7 | 0 | 2 | 0 | 0 | 9
IT Asset Management | Licenses | 11 | 9 | 0 | 2 | 0 | 0 | 11
IT Asset Management | Vendors | 1 | 1 | 0 | 0 | 0 | 0 | 1
IT Asset Management | Asset Dashboard | 4 | 2 | 0 | 2 | 0 | 0 | 4
IT Asset Management | Archive & Notifications | 10 | 7 | 0 | 3 | 0 | 0 | 10
IT Asset Management | Asset History | 2 | 2 | 0 | 0 | 0 | 0 | 2
IT Asset Management | Finance Controls | 16 | 13 | 0 | 3 | 0 | 0 | 16
IT Asset Management | QR Stickers | 3 | 0 | 0 | 3 | 0 | 0 | 3
IT Asset Management | Employee Assets | 1 | 0 | 0 | 1 | 0 | 0 | 1
IT Asset Management | History | 1 | 0 | 0 | 1 | 0 | 0 | 1
IT Asset Management | Masters | 1 | 0 | 0 | 1 | 0 | 0 | 1
IT Asset Management | User Master | 1 | 0 | 0 | 1 | 0 | 0 | 1
IT Asset Management | Responsive | 2 | 0 | 0 | 2 | 0 | 0 | 2
IT Asset Management | Performance | 1 | 0 | 0 | 1 | 0 | 0 | 1
IT Asset Management — subtotal |  | 115 | 82 | 0 | 33 | 0 | 0 | 115
Identity & Access Management | Central Identity (Ashika Portal SSO) | 21 | 17 | 0 | 4 | 0 | 0 | 21
Identity & Access Management | Role-based Access (RBAC) | 10 | 10 | 0 | 0 | 0 | 0 | 10
Identity & Access Management | API Security | 2 | 2 | 0 | 0 | 0 | 0 | 2
Identity & Access Management | Roles & Permissions | 1 | 0 | 0 | 1 | 0 | 0 | 1
Identity & Access Management — subtotal |  | 34 | 29 | 0 | 5 | 0 | 0 | 34
Grand total |  | 149 | 111 | 0 | 38 | 0 | 0 | 149
Automated pass rate | 100%
UAT pass rate (of executed) | 0%
How to use
Yellow cells on 'Test Cases' (UAT Result, Tester, Date, Remarks) are for the client's UAT team — pick Pass / Fail / Blocked / Not Run.
Columns J–K show the automated run done before delivery (API + browser). 'Manual (UAT)' rows are UI checks to execute by hand.
This Summary recalculates automatically from the Test Cases sheet.
Example: UAT Result = Pass, UAT Tester = 'IT Asset team', UAT Date = 2026-10-20, Remarks = 'OK on Chrome / Android'.
Portal sign-in cases need the Portal admin to register IT Hub, and the users created in IT Hub User Master with a role — see 'IT Hub Roles & Access'.

## Test Cases
Test ID | Module | Sub-module | Test Scenario | Pre-conditions | Test Steps (in the application) | Expected Result | Priority | Type | Automated Run (API / Browser) | Automated Run — Actual | UAT Result | UAT Tester | UAT Date | Defect / Remarks
AST-01 | IT Asset Management | Asset Registry | Register a new asset with an automatic tag | Signed in as an IT administrator (or a role with edit on this module). | Asset Registry › Add Asset: choose type Laptop (tag auto-fills), fill name, serial, vendor, location › Create › confirm. [API check: POST /api/assets with type Laptop, serial, vendor] | HTTP 201; tag LAP-####; trail entry "Registered" | High | Positive | Pass | As expected
AST-02 | IT Asset Management | Asset Registry | Duplicate serial number for same type is rejected | Signed in as an IT administrator (or a role with edit on this module). | Add Asset again with the same type and serial number. [API check: POST /api/assets with an existing serial] | HTTP 400 "already exists" | High | Negative | Pass | As expected
AST-03 | IT Asset Management | Asset Registry | New asset cannot start as Allocated | Signed in as an IT administrator (or a role with edit on this module). | (API rule) New assets can be In Stock / In Use / Under Maintenance / Retired only — status list in Add Asset. [API check: POST /api/assets with status Allocated] | HTTP 400 — use Issue instead | High | Negative | Pass | As expected
AST-04 | IT Asset Management | Asset Registry | Edit requires a reason comment | Signed in as an IT administrator (or a role with edit on this module). | Edit the asset, change Location, leave the comment empty, Save. [API check: PATCH /api/assets/:id without comment] | HTTP 400 asking for a comment | High | Negative | Pass | As expected
AST-05 | IT Asset Management | Asset Registry | Edit with comment records a field-level change trail | Signed in as an IT administrator (or a role with edit on this module). | Edit again with a comment, Save; open the asset › History & comments. [API check: PATCH location + comment] | HTTP 200; trail "Updated" with Location from→to and the comment | High | Positive | Pass | As expected
AST-06 | IT Asset Management | Asset Registry | Status cannot be changed through edit | Signed in as an IT administrator (or a role with edit on this module). | Edit form: status is not editable — use lifecycle buttons. [API check: PATCH status=Retired with comment] | Status unchanged (lifecycle actions only) | High | Negative | Pass | As expected
AST-07 | IT Asset Management | Asset Registry | Comment on an asset | Signed in as an IT administrator (or a role with edit on this module). | Asset › History & comments › add a comment. [API check: POST /api/asset-comments/:id] | HTTP 200/201 and visible in trail | High | Positive | Pass | As expected
AST-08 | IT Asset Management | Asset Register Upload | Upload validation rejects bad rows and saves nothing | Signed in as an IT administrator (or a role with edit on this module). | Upload Register with a file containing an invalid type, a bad date and a missing vendor. [API check: POST /api/assets/import (dry run) with invalid type, bad date, missing vendor] | errors listed per row/column; inserted=0 | High | Negative | Pass | As expected
AST-09 | IT Asset Management | Asset Register Upload | Valid upload imports, auto-tags and creates vendors | Signed in as an IT administrator (or a role with edit on this module). | Upload Register with 2 valid rows (one Allocated with Assigned To). [API check: POST /api/assets/import with 2 valid rows (dryRun false)] | inserted=2; tags generated | High | Positive | Pass | As expected
AST-10 | IT Asset Management | Asset Registry | Sample template rows are refused | Signed in as an IT administrator (or a role with edit on this module). | Upload the template without deleting the SAMPLE rows. [API check: Import a row with tag SAMPLE-001] | Row error "Sample row from the template" | High | Negative | Pass | As expected
LC-01 | IT Asset Management | Handovers | Issue an asset to an employee | Signed in as an IT administrator (or a role with edit on this module). | Handovers › Issue assets: pick an In Stock asset, employee details, Permanent, Good › Issue; print handover note. [API check: POST /api/assets/:id/issue (Permanent, condition Good)] | Status Allocated; handover HO-YYYY-##### created, acknowledgement Pending | High | Positive | Pass | As expected
LC-02 | IT Asset Management | Handovers | Temporary issue requires an expected return date | Signed in as an IT administrator (or a role with edit on this module). | Issue as Temporary / Loaner without an expected return date. [API check: Issue with allocationType Temporary and no return date] | HTTP 400 | High | Negative | Pass | As expected
LC-03 | IT Asset Management | Handovers | Allocated asset cannot be deleted | Signed in as an IT administrator (or a role with edit on this module). | Try to delete an Allocated asset. [API check: DELETE /api/assets/:id while Allocated] | HTTP 400 | High | Negative | Pass | As expected
LC-04 | IT Asset Management | Handovers | IT records the employee acknowledgement | Signed in as an IT administrator (or a role with edit on this module). | Handovers › Ack pending › mark acknowledged. [API check: POST /api/asset-allocations/:id/acknowledge] | ackStatus Acknowledged; trail entry | High | Positive | Pass | As expected
LC-05 | IT Asset Management | Handovers | Return needs a condition | Signed in as an IT administrator (or a role with edit on this module). | Return the asset without choosing a condition. [API check: POST /api/assets/:id/return without condition] | HTTP 400 | High | Negative | Pass | As expected
LC-06 | IT Asset Management | Handovers | Return the asset to stock | Signed in as an IT administrator (or a role with edit on this module). | Return the asset: condition Good, next status In Stock. [API check: POST return with condition Good, next In Stock] | Status In Stock; handover Returned | High | Positive | Pass | As expected
LC-07 | IT Asset Management | Lifecycle | Send to maintenance needs a reason | Signed in as an IT administrator (or a role with edit on this module). | Asset › Lifecycle › Send to maintenance without a reason. [API check: POST transition Under Maintenance without reason] | HTTP 400 | High | Negative | Pass | As expected
LC-08 | IT Asset Management | Lifecycle | Maintenance round trip | Signed in as an IT administrator (or a role with edit on this module). | Send to maintenance with a reason, then Repair completed. [API check: Transition → Under Maintenance (reason) → In Stock] | Both HTTP 200, statuses follow | High | Positive | Pass | As expected
LC-09 | IT Asset Management | Lifecycle | Invalid transition is blocked | Signed in as an IT administrator (or a role with edit on this module). | Try to dispose an In Stock asset directly. [API check: In Stock → Disposed directly] | HTTP 400 "Cannot move" | High | Negative | Pass | As expected
LC-10 | IT Asset Management | Lifecycle | Retire then dispose with certificate | Signed in as an IT administrator (or a role with edit on this module). | Retire an asset, then Dispose with method, certificate no. and value. [API check: Retired (reason) → Disposed (method, certificate, value)] | Status Disposed; disposal fields stored | High | Positive | Pass | As expected
LC-11 | IT Asset Management | My Assets | Employee sees and acknowledges own assets | Signed in as an IT administrator (or a role with edit on this module). | Issue an asset to your own email; open User menu › My Assets and acknowledge. [API check: Issue to the Portal user email; GET /api/my-assets as that user; acknowledge] | Asset listed; acknowledgement recorded | High | Positive | Pass | As expected
EMP-01 | IT Asset Management | Employee Mapping | Holder list comes from User Master with code and Internal/External tag | Signed in as an IT administrator (or a role with edit on this module). | Handovers › Issue assets › open the Employee box: each entry shows 'login email – EMP CODE' with an Internal / External tag; use the All / Internal / External filter. [API check: GET /api/asset-people] | Each person has employeeCode and userType; people without a code are not selectable | Medium | Positive | Pass | As expected
EMP-02 | IT Asset Management | Employee Mapping | Issue is linked by employee code — name/email taken from User Master | Signed in as an IT administrator (or a role with edit on this module). | Admin › User Master: add an External user with an employee code. Issue a laptop to them; check the handover and the asset show their code and 'External'. [API check: Issue with only employeeCode (external person)] | Handover has the master name, email, code and type External | Medium | Positive | Pass | As expected
EMP-03 | IT Asset Management | Employee Mapping | Unknown employee code is refused | Signed in as an IT administrator (or a role with edit on this module). | (API rule) Issuing with an employee code that is not in User Master is refused. [API check: Issue with employeeCode NOPE-999] | HTTP 400 "not in User Master" | Medium | Negative | Pass | As expected
EMP-04 | IT Asset Management | Employee Mapping | Person without an employee code cannot be issued assets | Signed in as an IT administrator (or a role with edit on this module). | In the Employee box, a person with no employee code is greyed out and cannot be selected. [API check: Issue to a User Master entry with no code (by userId)] | HTTP 400 "no Employee Code" | Medium | Negative | Pass | As expected
EMP-05 | IT Asset Management | Employee Mapping | Free-text holder (not in User Master) is refused | Signed in as an IT administrator (or a role with edit on this module). | (API rule) A typed name that is not in User Master cannot be issued assets. [API check: Issue with only userName / email] | HTTP 400 | Medium | Negative | Pass | As expected
EMP-06 | IT Asset Management | Employee Mapping | User Master: duplicate employee code rejected; blank code rejected on edit | Signed in as an IT administrator (or a role with edit on this module). | Admin › User Master: create a user with an employee code already in use; then edit a user and clear the code. [API check: POST /api/admin/users with an existing code; PATCH with blank code] | HTTP 400 both | Medium | Negative | Pass | As expected
EMP-07 | IT Asset Management | Employee Mapping | Register upload: Allocated rows need a User Master employee code | Signed in as an IT administrator (or a role with edit on this module). | Upload Register with an Allocated row without Employee Code and one with an unknown code. [API check: Import dry-run: Allocated without code, with unknown code] | Row errors on Employee Code | Medium | Positive | Pass | As expected
EMP-08 | IT Asset Management | Bulk Assignment | Bulk assign validates every row first | Signed in as an IT administrator (or a role with edit on this module). | Handovers › Bulk assign (Excel) › upload a sheet with an unknown tag, an unknown employee code and a Temporary row without return date. [API check: POST /api/asset-handovers/bulk-assign (dry run) with unknown tag, unknown code, temporary without return date] | Errors per row; nothing applied | Medium | Positive | Pass | As expected
EMP-09 | IT Asset Management | Bulk Assignment | Bulk assign: issue, reassign and unchanged in one upload | Signed in as an IT administrator (or a role with edit on this module). | Handovers › Bulk assign › Download; change Employee Code on two assets (one in stock, one held by someone else), keep one unchanged › Upload › Apply. [API check: Upload: spare → EMP-QA-02 (issue), external laptop → EMP-QA-02 (reassign), and a row matching its current holder (unchanged)] | issue=1, reassign=1, unchanged=1; old handover closed; new handovers created | Medium | Positive | Pass | As expected
EMP-10 | IT Asset Management | Employee Mapping | Employee Assets groups by employee code with Internal/External | Signed in as an IT administrator (or a role with edit on this module). | IT Assets › Employee Assets: each person is listed once with code and Internal / External tag. [API check: GET /api/asset-holders] | One row per code; userType present | Medium | Positive | Pass | As expected
EMP-11 | IT Asset Management | Employee Mapping | Role assignment is admin-only | Signed in as an IT administrator (or a role with edit on this module). | (Security) Only an administrator can change a user's access roles. [API check: PUT /api/user-roles/:id as a non-admin (Asset Manager)] | HTTP 403 | Medium | Positive | Pass | As expected
AUD-01 | IT Asset Management | Physical Audit | Plan an audit for a location | Signed in as an IT administrator (or a role with edit on this module). | Physical Audit › Plan audit: name, location Worli › Plan. [API check: POST /api/asset-audits {name, locations:[Worli]}] | HTTP 201; AUD-YYYY-####; expected count > 0 | Medium | Positive | Pass | As expected
AUD-02 | IT Asset Management | Physical Audit | Scanning before start is refused | Signed in as an IT administrator (or a role with edit on this module). | Open the planned audit and try to scan before Start. [API check: POST scan while Planned] | HTTP 400 "Start the audit" | Medium | Negative | Pass | As expected
AUD-03 | IT Asset Management | Physical Audit | Scan a QR sticker URL | Signed in as an IT administrator (or a role with edit on this module). | Start the audit, choose location, scan a QR sticker with the phone camera (or type the tag). [API check: Start; POST scan with https://host/a/<TAG>] | Item marked Found / Location mismatch / Not in scope | Medium | Positive | Pass | As expected
AUD-04 | IT Asset Management | Physical Audit | Complete marks unscanned as Missing | Signed in as an IT administrator (or a role with edit on this module). | Complete the audit; check the Missing tab and report. [API check: POST complete] | Status Completed; summary has Missing count | Medium | Positive | Pass | As expected
CT-01 | IT Asset Management | Contracts & AMC | Create an AMC covering assets | Signed in as an IT administrator (or a role with edit on this module). | Contracts & AMC › New contract: Comprehensive AMC, vendor, dates, value, select assets › Create. [API check: POST /api/asset-contracts with dates, value, assetIds] | HTTP 201; CT-YYYY-####; assets covered; trail "Contract" | Medium | Positive | Pass | As expected
CT-02 | IT Asset Management | Contracts & AMC | End date before start date is rejected | Signed in as an IT administrator (or a role with edit on this module). | New contract with end date before start date. [API check: POST contract with end < start] | HTTP 400 | Medium | Negative | Pass | As expected
CT-03 | IT Asset Management | Contracts & AMC | Contract within notice period shows as Expiring | Signed in as an IT administrator (or a role with edit on this module). | Check the contract status pill when the end date is within the reminder days. [API check: GET /api/asset-contracts] | state=Expiring for an end date within 30 days | Medium | Positive | Pass | state=Expiring, daysLeft=16
CT-04 | IT Asset Management | Contracts & AMC | Renew a contract — assets carry over, old one keeps cover till its end | Signed in as an IT administrator (or a role with edit on this module). | Open the contract › Renew: new dates/value › Confirm; open an asset › Warranty & finance. [API check: POST /api/asset-contracts/:id/renew] | New contract created; old status Renewed; asset still covered today | Medium | Positive | Pass | As expected
CT-05 | IT Asset Management | Contracts & AMC | A renewed contract cannot be renewed again | Signed in as an IT administrator (or a role with edit on this module). | Open the old (Renewed) contract — Renew is not offered. [API check: POST renew on the old contract] | HTTP 400 | Medium | Negative | Pass | As expected
FIN-01 | IT Asset Management | Depreciation | Finance upload validates before saving | Signed in as an IT administrator (or a role with edit on this module). | Depreciation › Update purchase & cost › upload a sheet with a bad date and an unknown tag. [API check: POST /api/assets/finance-update (dry run) with a bad date and unknown tag] | Errors listed; nothing updated | High | Positive | Pass | As expected
FIN-02 | IT Asset Management | Depreciation | Finance upload fills purchase date, cost and warranty | Signed in as an IT administrator (or a role with edit on this module). | Download 'Missing only' sheet, fill purchase date, cost, warranty for one asset, upload, Apply. [API check: POST finance-update (apply) for the QA asset] | updated=1; trail "Updated" with the changes | High | Positive | Pass | As expected
FIN-03 | IT Asset Management | Depreciation | SLM schedule follows Schedule II (3 yrs, 5% residual, Indian FY) | Signed in as an IT administrator (or a role with edit on this module). | Depreciation › Register › click the asset › schedule (₹1,00,000 from 01-Apr-2024, SLM 3y). [API check: GET /api/asset-depreciation/asset/:id] | FY 2024-25 dep ₹31,666.67; closing after 3 yrs = ₹5,000 | High | Positive | Pass | As expected
FIN-04 | IT Asset Management | Depreciation | WDV override uses the Schedule II rate (63.16% for 3 yrs) | Signed in as an IT administrator (or a role with edit on this module). | Edit the asset: Depreciation method WDV › view schedule; then set back to 'As per rule'. [API check: PATCH asset depreciationMethod=WDV; GET schedule] | First full year dep ≈ 63.16% of opening | High | Positive | Pass | As expected
FIN-05 | IT Asset Management | Depreciation | Fixed-asset register balances (opening + additions − deletions = closing) | Signed in as an IT administrator (or a role with edit on this module). | Depreciation › Register for FY 2026-27 › Export register; check totals. [API check: GET /api/asset-depreciation/register?fy=2026] | Gross & accumulated blocks reconcile | High | Positive | Pass | As expected
FIN-06 | IT Asset Management | Depreciation | Disposed asset shows as deletion with gain/loss | Signed in as an IT administrator (or a role with edit on this module). | Register: find the disposed asset (deleted this year, gain/loss). [API check: Register for FY of disposal] | deletions include asset cost; gainLoss computed | High | Positive | Pass | As expected
FIN-07 | IT Asset Management | Depreciation | Rule validation | Signed in as an IT administrator (or a role with edit on this module). | Depreciation › Rules: set useful life 0 for a type › Save. [API check: PUT rule with useful life 0] | HTTP 400 | High | Negative | Pass | As expected
LIC-01 | IT Asset Management | Licenses | Add a per-user subscription | Signed in as an IT administrator (or a role with edit on this module). | Licenses › Add license: Per User, 3 seats, ₹60,000, dates › Add. [API check: POST /api/asset-licenses (3 seats, ₹60,000)] | HTTP 201 | High | Positive | Pass | As expected
LIC-02 | IT Asset Management | Licenses | Assign seats to users; duplicates skipped | Signed in as an IT administrator (or a role with edit on this module). | Open license › Assign to users: paste 4 lines incl. one duplicate › Assign. [API check: POST assignments with 4 users incl. one duplicate] | added=3, skipped 1; tracking=Assignments | High | Positive | Pass | As expected
LIC-03 | IT Asset Management | Licenses | Over-assignment flags Under-licensed with true-up exposure | Signed in as an IT administrator (or a role with edit on this module). | Assign to devices: 1 laptop (4th seat) › confirm warning. [API check: Assign the license to 1 device (4th seat)] | compliance Under-licensed; exposure ₹20,000 | High | Positive | Pass | As expected
LIC-04 | IT Asset Management | Licenses | Revoke needs a reason | Signed in as an IT administrator (or a role with edit on this module). | Revoke a seat with an empty reason. [API check: POST revoke with empty reason] | HTTP 400 | High | Negative | Pass | As expected
LIC-05 | IT Asset Management | Licenses | Seats on a disposed/retired device appear as reclaim candidates | Signed in as an IT administrator (or a role with edit on this module). | Retire the laptop holding a seat; Licenses › Compliance › Reclaim candidates. [API check: Retire the device; GET compliance] | Reclaim list contains the device seat | High | Positive | Pass | As expected
LIC-06 | IT Asset Management | Licenses | Revoke frees the seat and restores compliance | Signed in as an IT administrator (or a role with edit on this module). | Reclaim the seat with a reason. [API check: POST revoke with reason] | compliance Compliant; trail entry on the device | High | Positive | Pass | As expected
LIC-07 | IT Asset Management | Licenses | License with assigned seats cannot be deleted | Signed in as an IT administrator (or a role with edit on this module). | Delete the license while seats are assigned. [API check: DELETE /api/asset-licenses/:id] | HTTP 400 | High | Negative | Pass | As expected
LIC-08 | IT Asset Management | Licenses | Expired license still in use is flagged | Signed in as an IT administrator (or a role with edit on this module). | Edit the license expiry to a past date. [API check: Set expiry in the past] | compliance "Expired – in use" | High | Positive | Pass | As expected
LIC-09 | IT Asset Management | Licenses | Edit form round-trip (dates/timestamps) works | Signed in as an IT administrator (or a role with edit on this module). | Edit any license and Save without changes (regression of 'toISOString' error). [API check: PATCH the full record as returned by GET] | HTTP 200 — no "toISOString" error | High | Positive | Pass | As expected
VEN-01 | IT Asset Management | Vendors | Vendor create / edit / delete | Signed in as an IT administrator (or a role with edit on this module). | Vendors › Add, Edit, Delete a vendor. [API check: POST, PATCH, DELETE /api/asset-vendors] | HTTP 201, 200, 204 | Medium | Positive | Pass | As expected
DB-01 | IT Asset Management | Asset Dashboard | Dashboard aggregates all modules | Assets loaded. | Open Asset Dashboard; click each tile and 'Needs attention' row. [API check: GET /api/asset-dashboard] | inventory, handovers, warranty, contracts, finance, licenses, audits, attention, activity present | Medium | Positive | Pass | As expected
DB-02 | IT Asset Management | Asset Dashboard | Dashboard is permission-checked | Assets loaded. | Sign in as a user whose IT Hub role has Asset Registry but not Asset Dashboard; open /assets. [API check: Sign in as a user whose IT Hub role lacks "Asset Dashboard"; GET /api/asset-dashboard] | HTTP 403 | Medium | Positive | Pass | As expected
ARC-01 | IT Asset Management | Archive & Notifications | Notification recipients: validation and save | Signed in as an IT administrator (or a role with edit on this module). | Admin › Archive & Notifications › Email notifications: enter 'a@x.com, bad-email' for Asset register upload › Save; then fix it › Save. [API check: PUT /api/notification-rules/asset_register_upload with an invalid then valid comma-separated list] | Invalid → HTTP 400; valid saved | Medium | Negative | Pass | As expected
ARC-02 | IT Asset Management | Archive & Notifications | Register upload is archived as one batch and emailed | Signed in as an IT administrator (or a role with edit on this module). | Upload a register with a department and location not yet in Master Data › check the preview, Import; open Admin › Archive and Master Data. [API check: Upload 1 asset with a new department and location] | Archive batch ARC-YYYY-#####; email logged with Excel; new masters created | Medium | Positive | Pass | As expected
ARC-03 | IT Asset Management | Archive & Notifications | Archive batch Excel has Change Summary, New and Old register | Signed in as an IT administrator (or a role with edit on this module). | Admin › Archive & Notifications › Archive › Excel on the upload batch. [API check: GET /api/data-archive/:id/excel] | xlsx with sheets Change Summary, New Asset Register, Old Asset Register, Uploaded Rows, Batch Info | Medium | Positive | Pass | As expected
ARC-04 | IT Asset Management | Archive & Notifications | Bulk assignment and finance uploads are archived too | Signed in as an IT administrator (or a role with edit on this module). | Run Handovers › Bulk assign and Depreciation › Update purchase & cost; check Admin › Archive. [API check: Run a bulk assign and a finance upload] | Both responses carry an archive batch number | Medium | Positive | Pass | As expected
HIS-01 | IT Asset Management | Asset History | History is read-only in the database | Signed in as an IT administrator (or a role with edit on this module). | (Database rule) Try to change or delete a history row directly in the database. [API check: UPDATE / DELETE on asset_transactions] | Both rejected by the database | Medium | Positive | Pass | As expected
HIS-02 | IT Asset Management | Asset History | History is newest first with movement details | Signed in as an IT administrator (or a role with edit on this module). | Open an issued asset › History & comments. [API check: GET /api/asset-transactions?assetId= for an issued asset] | Descending order; Issued entry carries Holder from → to | Medium | Positive | Pass | As expected
MC-01 | IT Asset Management | Finance Controls | A person cannot approve their own change | Signed in as an IT administrator (or a role with edit on this module). | Depreciation › Rules: change a rule › Submit. Open Approvals as the same user (no Approve button), then sign in as Finance › Approvals › Approve. [API check: Submit a rule change; approve it as the same user, then as a different Finance user] | Own approval HTTP 403; other approver applies it | High | Negative | Pass | As expected
MC-02 | IT Asset Management | Finance Controls | Reject needs a reason; the maker can cancel | Signed in as an IT administrator (or a role with edit on this module). | Depreciation › Approvals › Reject (reason box must be filled); raise another change and click Withdraw as the requester. [API check: Reject without / with reason; raise and cancel another] | HTTP 400 then Rejected; Cancelled | High | Negative | Pass | As expected
MC-03 | IT Asset Management | Finance Controls | IT Asset Manager can submit a cost upload but cannot approve | Signed in as an IT administrator (or a role with edit on this module). | Sign in as IT Asset Manager › Depreciation › Update purchase & cost › upload sheet › Submit for approval; open Approvals (no Approve button). [API check: POST finance-update as IT Asset Manager; try to approve] | HTTP 202 submit; HTTP 403 approve | High | Negative | Pass | As expected
MC-04 | IT Asset Management | Finance Controls | Cost edit from the asset form waits for approval | Signed in as an IT administrator (or a role with edit on this module). | Asset Registry › Edit an asset › change Cost and Notes › comment › Save. Notes saved at once; toast shows request no.; cost changes after Finance approves. [API check: PATCH cost with a comment; read the asset; approve] | Cost unchanged until approved; other fields saved at once | High | Positive | Pass | As expected
FYC-01 | IT Asset Management | Finance Controls | Close FY 2025-26 freezes its register | Signed in as an IT administrator (or a role with edit on this module). | Depreciation › Year-end close › Close FY 2025-26 › add note › confirm. Register tab › FY 2025-26 shows 'Closed — frozen register'. [API check: GET register FY2025; POST close; GET register again] | Locked=true; totals identical; archive batch + email logged | High | Positive | Pass | As expected
FYC-02 | IT Asset Management | Finance Controls | Nothing can be back-dated into a closed year | Signed in as an IT administrator (or a role with edit on this module). | After closing: register an asset with purchase date in the closed year and a cost; edit cost of an asset bought in the closed year; dispose with a closed-year date. [API check: Create asset dated 2025-06-01 with cost; change cost of a locked asset; delete it; dispose with a 2026-03 date] | All HTTP 409 / validation errors | High | Positive | Pass | As expected
FYC-03 | IT Asset Management | Finance Controls | Rule change after close applies only to open years | Signed in as an IT administrator (or a role with edit on this module). | After closing: change the Laptop rule (approve it). Register › closed year totals unchanged; current year depreciation recalculated. [API check: Approve Laptop life 3 → 5 years; compare FY 2025-26 and FY 2026-27] | Closed year unchanged; open year depreciation recalculated from frozen book value | High | Positive | Pass | FY25 304279.88 unchanged; FY26 185659.98 → 69731.19
DSP-01 | IT Asset Management | Finance Controls | Disposal records book value and profit / loss | Signed in as an IT administrator (or a role with edit on this module). | Asset › Retire › Dispose: enter value realised; panel shows book value and profit / loss before confirming. Depreciation › Disposals P&L lists it. [API check: Dispose (sale ₹5,000) an asset bought 2026-04-10 for ₹30,000] | Book value from schedule; gain/loss = sale − book; listed in Disposals report | High | Positive | Pass | book ₹24820.55, P/L ₹-19820.55
DSP-02 | IT Asset Management | Finance Controls | Lost / stolen is written off and reversed when found | Signed in as an IT administrator (or a role with edit on this module). | Asset › Report lost / stolen: panel shows write-off loss = book value. Then mark Found: the write-off is reversed. [API check: Report lost; read asset; mark found] | Write-off loss = book value; found clears the write-off | High | Positive | Pass | As expected
JRN-01 | IT Asset Management | Finance Controls | Monthly journal balances (Dr = Cr) | Signed in as an IT administrator (or a role with edit on this module). | Depreciation › Monthly journal › pick last month: Debit total = Credit total; 'Balanced' badge. [API check: GET journal for last month] | Lines present; total debit = total credit; ledgers per asset type | High | Positive | Pass | Dr = Cr = ₹27784.24
JRN-02 | IT Asset Management | Finance Controls | Journal export is archived and emailed as Excel | Signed in as an IT administrator (or a role with edit on this module). | Monthly journal › Export & email › Excel downloads (Journal (Tally), Asset Depreciation, Disposals); Admin › Archive lists the batch; exporting again is marked re-export. [API check: POST journal/export; download the batch Excel] | Batch ARC-…; sheets Journal (Tally) / Asset Depreciation / Disposals; email outbox entry | High | Positive | Pass | As expected
JRN-03 | IT Asset Management | Finance Controls | GL ledger names change through approval | Signed in as an IT administrator (or a role with edit on this module). | Monthly journal › GL ledgers › rename a ledger › Submit for approval; approve as Finance; name changes in the journal. [API check: PUT ledgers (loss ledger renamed); approve] | HTTP 202, then the new name appears | High | Positive | Pass | As expected
FYC-04 | IT Asset Management | Finance Controls | Only an administrator can reopen, with a reason | Signed in as an IT administrator (or a role with edit on this module). | Year-end close › Reopen (IT Asset Manager: no button / 403); as admin, reason is mandatory; year shows Reopened. [API check: POST reopen as IT Asset Manager; as admin without / with reason] | 403; 400; 200 and the year is open again | High | Positive | Pass | As expected
ARC-05 | IT Asset Management | Archive & Notifications | Clear all moves everything to the archive (no data loss) | Signed in as an IT administrator (or a role with edit on this module). | Asset Registry › Clear All Data › confirm twice; check Admin › Archive. [API check: POST /api/assets/purge] | Register empty; archive batch kind asset_clear with all tables | Medium | Positive | Pass | As expected
ARC-06 | IT Asset Management | Archive & Notifications | Restore a cleared batch with ids and full history | Signed in as an IT administrator (or a role with edit on this module). | Admin › Archive › Restore on the 'Asset data cleared' batch. [API check: POST /api/data-archive/:id/restore] | Same asset count and history count back; second restore refused | Medium | Positive | Pass | As expected
ARC-07 | IT Asset Management | Archive & Notifications | Archive and notification settings are admin-only | Signed in as an IT administrator (or a role with edit on this module). | Sign in as an IT Asset Manager and open /admin/archive. [API check: GET /api/data-archive and PUT /api/notification-rules as IT Asset Manager] | HTTP 403 | Medium | Positive | Pass | As expected
SSO-01 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Login page discovers Ashika Portal sign-in | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Open https://ithub-uat.niytri.com/login. [API check: GET /api/auth/central/config] | enabled=true, localLogin=admin, button label returned | High | Positive | Pass | As expected
SSO-02 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Break-glass: local administrator can still sign in with password | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | On the login page click 'Administrator sign-in (break-glass)', enter the local admin email + password, Sign In. [API check: POST /api/auth/login as local admin] | HTTP 200; /auth/me identitySource=local | High | Positive | Pass | As expected
SSO-03 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Local non-admin password login is blocked when Central Identity is on | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Click 'Administrator sign-in', enter a NON-admin local user's email + password, Sign In. [API check: POST /api/auth/login as a local non-admin user] | HTTP 403 with "Sign in with Ashika Portal" message | High | Negative | Pass | As expected
SSO-04 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Registered IT Hub admin signs in through the Portal (authorize → code → token) | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Admin › User Master: make sure the user exists (same email as the Portal) with role Admin. Click 'Sign in with Ashika Portal' and sign in on the Portal. [API check: Start /api/auth/central/login; Portal authenticates; IT Hub exchanges the code] | Lands on requested page; /auth/me role=admin (from IT Hub), identitySource=central | High | Positive | Pass | As expected
SSO-05 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Portal-authenticated person NOT registered in IT Hub is refused | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Sign in via the Portal as a person who is NOT in IT Hub User Master. [API check: Sign in via Portal as a person with no IT Hub user record] | Redirect to /login?sso_error=not_registered; no user created; no session | High | Negative | Pass | As expected
SSO-06 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Registered user with NO IT Hub role is refused | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Admin › User Master: create the user with NO role. Sign in via the Portal as that user. [API check: Sign in via Portal as a user present in IT Hub without any role] | Redirect to /login?sso_error=no_role; no session | High | Negative | Pass | As expected
SSO-14 | Identity & Access Management | Central Identity (Ashika Portal SSO) | User disabled in IT Hub is refused even if the Portal allows | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Admin › User Master: deactivate a user. That user signs in via the Portal. [API check: Deactivate in User Master; sign in via Portal] | Redirect to /login?sso_error=account_disabled | High | Negative | Pass | As expected
SSO-15 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Access comes from the IT Hub role, not the Portal role | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Admin › User Master: give a user only the role 'Asset Viewer'. Sign in via the Portal as that user and check the IT Assets menu. [API check: Sign in via Portal as a user mapped to IT Hub role "Asset Viewer"] | /auth/me shows read on assets + asset_registry only (Portal permissions ignored) | High | Positive | Pass | As expected
RBAC-01 | Identity & Access Management | Role-based Access (RBAC) | Viewer can read the asset register | Users mapped to IT Hub roles (see 'IT Hub Roles & Access'). | As the view-only user open IT Assets › Asset Registry. [API check: GET /api/assets as Asset Viewer] | HTTP 200 | High | Positive | Pass | As expected
RBAC-02 | Identity & Access Management | Role-based Access (RBAC) | Viewer cannot create an asset | Users mapped to IT Hub roles (see 'IT Hub Roles & Access'). | As the view-only user look for 'Add Asset' / 'Upload Register' / Edit icons. [API check: POST /api/assets as Asset Viewer] | HTTP 403 "view-only access" | High | Negative | Pass | As expected
RBAC-03 | Identity & Access Management | Role-based Access (RBAC) | Viewer cannot open a module not in the IT Hub role | Users mapped to IT Hub roles (see 'IT Hub Roles & Access'). | As the view-only user type /asset-contracts in the address bar. [API check: GET /api/asset-contracts as Asset Viewer] | HTTP 403 | High | Negative | Pass | As expected
RBAC-04 | Identity & Access Management | Role-based Access (RBAC) | Viewer cannot see the Physical Audit module | Users mapped to IT Hub roles (see 'IT Hub Roles & Access'). | As the view-only user type /asset-audits in the address bar. [API check: GET /api/asset-audits] | HTTP 403 | High | Negative | Pass | As expected
RBAC-05 | Identity & Access Management | Role-based Access (RBAC) | Viewer cannot purge asset data (admin only) | Users mapped to IT Hub roles (see 'IT Hub Roles & Access'). | As the view-only user look for 'Clear All Data' in Asset Registry. [API check: POST /api/assets/purge] | HTTP 403 | High | Negative | Pass | As expected
RBAC-06 | Identity & Access Management | Role-based Access (RBAC) | IT Asset Manager role can create and edit assets | Users mapped to IT Hub roles (see 'IT Hub Roles & Access'). | Sign in as a user with IT Hub role 'IT Asset Manager'. Add an asset, then edit its location with a comment. [API check: Sign in as a user with IT Hub role "IT Asset Manager"; add an asset; edit with comment] | HTTP 201 then 200 | High | Positive | Pass | As expected
RBAC-07 | Identity & Access Management | Role-based Access (RBAC) | IT Asset Manager can issue (asset_allocations: write) | Users mapped to IT Hub roles (see 'IT Hub Roles & Access'). | As the same user open Handovers › Issue assets and issue the asset. [API check: POST /api/assets/:id/issue] | HTTP 200/201 | High | Positive | Pass | As expected
RBAC-08 | Identity & Access Management | Role-based Access (RBAC) | IT Asset Manager cannot change depreciation rules (read only in role) | Users mapped to IT Hub roles (see 'IT Hub Roles & Access'). | As the same user open /asset-depreciation (not in role). [API check: PUT /api/asset-depreciation/rules/1] | HTTP 403 | High | Negative | Pass | As expected
RBAC-09 | Identity & Access Management | Role-based Access (RBAC) | Shared reference data: vendor list readable with any asset access | Users mapped to IT Hub roles (see 'IT Hub Roles & Access'). | As the same user open Add Asset — the Vendor list loads. [API check: GET /api/asset-vendors] | HTTP 200 | High | Positive | Pass | As expected
SSO-07 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Role change in IT Hub applies without re-login | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Admin › User Master: add role 'IT Asset Manager' to the view-only user. The user refreshes and adds an asset (no re-login). [API check: Admin › User Master: add "IT Asset Manager" to the viewer; viewer adds an asset] | Create succeeds (HTTP 201) immediately | High | Positive | Pass | As expected
SSO-16 | Identity & Access Management | Central Identity (Ashika Portal SSO) | All IT Hub roles removed → session ends | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | While the user is signed in, remove all their roles in User Master; the user clicks anything after a minute. [API check: Remove every role from the user in User Master; user clicks anything] | HTTP 401 code=central_no_role at the next check; back to login | High | Positive | Pass | As expected
SSO-08 | Identity & Access Management | Central Identity (Ashika Portal SSO) | User disabled in the Portal is locked out | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | In the Portal disable the user. Within 1 minute click anything in IT Hub. [API check: Disable the user in the Portal; next request after re-validation] | HTTP 401 code=central_inactive; session destroyed | High | Positive | Pass | As expected
SSO-09 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Portal refuses a user not allowed for IT Hub | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Sign in via Portal as a user the Portal does not allow into IT Hub (if the Portal restricts apps). [API check: Sign in as a user the Portal does not allow for this app] | Redirect to /login?sso_error=access_denied, no session | High | Positive | Pass | As expected
SSO-10 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Tampered / replayed callback is rejected (state check) | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Open /api/auth/central/callback?code=abc&state=forged directly. [API check: GET /api/auth/central/callback?code=x&state=forged] | Redirect to /login?sso_error=invalid_state | High | Negative | Pass | As expected
SSO-11 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Open-redirect protection on "next" | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Open /api/auth/central/login?next=//example.com and complete sign-in. [API check: GET /api/auth/central/login?next=//evil.example] | After login lands on "/" not an external site | High | Negative | Pass | As expected
SSO-12 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Logout ends the IT Hub session | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | User menu › Logout, then press Back / open any page. [API check: POST /api/auth/logout then GET /auth/me] | HTTP 401 after logout | High | Positive | Pass | As expected
SSO-13 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Client secret never reaches the browser | IT Hub registered in Ashika Portal (sso_apps); CENTRAL_SSO_* set on the server; users created in IT Hub User Master. | Browser DevTools › Network: inspect login traffic for the client secret. [API check: GET /api/auth/central/config and the login redirect URL] | No client_secret in any browser-facing response | High | Negative | Pass | As expected
SEC-01 | Identity & Access Management | API Security | All asset APIs require sign-in | Server deployed over HTTPS. | Open /api/assets in a private window (not signed in). [API check: GET /api/assets, /api/asset-contracts without a session] | HTTP 401 | High | Positive | Pass | As expected
SEC-02 | Identity & Access Management | API Security | Direct page URL /assets loads the app (no static-folder redirect) | Server deployed over HTTPS. | Open https://ithub-uat.niytri.com/assets directly / press F5 on Asset Dashboard. [API check: GET /assets] | HTTP 200 HTML, no 301 to /assets/ | High | Positive | Pass | As expected
RBAC-10 | Identity & Access Management | Role-based Access (RBAC) | Menu & page access follow the IT Hub role (browser) | Central Identity enabled; Portal roles configured. | Sign in via Portal as users mapped to IT Asset Manager, Asset Viewer and Admin; open every IT Asset page. | Pages outside the role show 'You don't have access to this page'; Add/Edit buttons only where the role has edit. | High | Positive | Pass | IT Asset Manager: edit everywhere except Depreciation (view). Asset Viewer: view Dashboard + Registry only. Admin: all. No console errors.
RBAC-11 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Login page shows Ashika Portal sign-in (browser) | Central Identity enabled; Portal roles configured. | Open /login with Central Identity enabled. | 'Sign in with Ashika Portal' button; password form hidden behind 'Administrator sign-in (break-glass)'. | High | Positive | Pass | As expected (screenshot verified).
UI-01 | IT Asset Management | QR Stickers | Print QR stickers (3 formats) | Signed in with the right role; sample data loaded. | Asset Registry › QR Stickers › choose 50×25 mm, A4 24-up, 85×54 mm › Print. | Stickers show logo, tag, name, serial and a scannable QR; layout fits the label size. | High | Functional | Manual (UAT)
UI-02 | IT Asset Management | QR Stickers | Scan sticker with phone camera (not signed in) | Signed in with the right role; sample data loaded. | Scan a sticker with the phone camera app. | Opens IT Hub login; after sign-in lands on that asset's page. | High | Functional | Manual (UAT)
UI-03 | IT Asset Management | QR Stickers | In-app scanner | Signed in with the right role; sample data loaded. | Open /asset-scan on a phone › allow camera › scan a sticker. | Asset details open; repeat scans within 20 s are ignored in audits. | High | Functional | Manual (UAT)
UI-04 | IT Asset Management | Asset Registry | Search, filters and pagination | Signed in with the right role; sample data loaded. | Search by tag/serial/user; filter type, status, department; page through. | Results update instantly; counts correct. | Medium | Functional | Manual (UAT)
UI-05 | IT Asset Management | Asset Registry | Export CSV | Signed in with the right role; sample data loaded. | Asset Registry › Export CSV. | CSV opens in Excel with all listed assets. | Medium | Functional | Manual (UAT)
UI-06 | IT Asset Management | Asset Register Upload | Download template | Signed in with the right role; sample data loaded. | Upload Register › Template. | Workbook with columns, 3 sample rows, Instructions and Allowed Values sheets. | Medium | Functional | Manual (UAT)
UI-07 | IT Asset Management | Asset Registry | In-app confirmations | Signed in with the right role; sample data loaded. | Create, edit, delete, issue, return, renew, revoke. | Every action shows an in-app confirmation box (never a browser pop-up). | High | Usability | Manual (UAT)
UI-08 | IT Asset Management | Asset Registry | Clear All Data (admin only) | Signed in with the right role; sample data loaded. | As full admin: Asset Registry › Clear All Data › type the confirmation text. | All asset data cleared after typed confirmation; non-admins never see the button. | High | Security | Manual (UAT)
UI-09 | IT Asset Management | Handovers | Handover note print | Signed in with the right role; sample data loaded. | Handovers › print icon on a handover. | Printable note with handover no., asset, accessories, signatures. | Medium | Functional | Manual (UAT)
UI-10 | IT Asset Management | Handovers | Overdue temporary returns | Signed in with the right role; sample data loaded. | Issue as Temporary with a past return date › Handovers › Overdue returns tab. | Listed in red; counted on the dashboard. | Medium | Functional | Manual (UAT)
UI-11 | IT Asset Management | Employee Assets | Employee view | Signed in with the right role; sample data loaded. | Employee Assets › select an employee. | All assets held, with handover numbers and acknowledgement status. | Medium | Functional | Manual (UAT)
UI-12 | IT Asset Management | History | Asset history trail | Signed in with the right role; sample data loaded. | Open any asset › History & comments. | Every change shows who, when, what changed (from → to) and the comment. | High | Audit | Manual (UAT)
UI-13 | IT Asset Management | Physical Audit | Location mismatch & apply | Signed in with the right role; sample data loaded. | Scan an asset at a different location; Complete with 'update locations'. | Marked Location mismatch; register location corrected and logged. | Medium | Functional | Manual (UAT)
UI-14 | IT Asset Management | Contracts & AMC | Warranty coverage tabs | Signed in with the right role; sample data loaded. | Contracts & AMC › Warranty coverage › At risk / Expiring / Expired / Covered / Not recorded. | Each tab lists the right assets; Export works. | Medium | Functional | Manual (UAT)
UI-15 | IT Asset Management | Contracts & AMC | Add / remove covered assets | Signed in with the right role; sample data loaded. | Open a contract › Add assets / remove one. | Coverage updates; each asset's history shows the change. | Medium | Functional | Manual (UAT)
UI-16 | IT Asset Management | Depreciation | FY selector | Signed in with the right role; sample data loaded. | Depreciation › Register › switch FY. | Figures change per FY; current FY shows 'year to date'. | Medium | Functional | Manual (UAT)
UI-17 | IT Asset Management | Depreciation | Rule change recalculates | Signed in with the right role; sample data loaded. | Rules › change Laptop to 4 years › Save. | Confirmation shown; register and book values recalculate. | Medium | Functional | Manual (UAT)
UI-18 | IT Asset Management | Licenses | Compliance report export | Signed in with the right role; sample data loaded. | Licenses › Compliance › Export report. | CSV with entitlement, use, shortfall, exposure, unused spend. | Medium | Functional | Manual (UAT)
UI-19 | IT Asset Management | Licenses | Seat utilisation bars | Signed in with the right role; sample data loaded. | Licenses list. | Bars red when short, amber ≥ 90 %, numbers match seats. | Low | Usability | Manual (UAT)
UI-20 | IT Asset Management | Asset Dashboard | Tiles and drill-down | Signed in with the right role; sample data loaded. | Dashboard › click each tile and list row. | Opens the matching page/tab with the same numbers. | High | Functional | Manual (UAT)
UI-21 | IT Asset Management | Asset Dashboard | Empty state | Signed in with the right role; sample data loaded. | Fresh database with no assets. | Friendly 'No assets yet' with a link to Asset Registry. | Low | Usability | Manual (UAT)
UI-22 | IT Asset Management | Masters | Asset masters | Signed in with the right role; sample data loaded. | Admin › Master Data › IT Asset Management. | Asset type, status, license type/status, location, OS, contract type lists populated and editable. | Medium | Functional | Manual (UAT)
UI-32 | IT Asset Management | Archive & Notifications | Upload email received with Excel | Signed in with the right role; sample data loaded. | Set your email for Asset register upload; upload a register (server mail configured). | Email arrives with the summary and an Excel: Change Summary, New Asset Register, Old Asset Register, Uploaded Rows. | High | Functional | Manual (UAT)
UI-33 | IT Asset Management | Archive & Notifications | KPI upload email | Signed in with the right role; sample data loaded. | Set recipients for KPI upload; upload a KPI set. | Email with Change Summary, New KPI Set, Old KPI Set; batch in Admin › Archive. | Medium | Functional | Manual (UAT)
UI-34 | IT Asset Management | Asset Registry | Department & Location drop-downs | Signed in with the right role; sample data loaded. | Asset Registry › Add / Edit asset; Handovers › Issue. | Department and Location are drop-downs from Master Data; old free-text values still shown as 'not in master'. | Medium | Functional | Manual (UAT)
UI-35 | IT Asset Management | Archive & Notifications | Send test email | Signed in with the right role; sample data loaded. | Admin › Archive & Notifications › Send test to your address. | Test email arrives; Email log shows Sent (or a clear error if mail is not configured). | Medium | Functional | Manual (UAT)
UI-31 | IT Asset Management | User Master | Access roles on the user form | Signed in with the right role; sample data loaded. | Admin › User Master › Edit user › Access roles: tick IT Asset Admin › Update; sign in as that user. | The user sees and can edit every IT Asset screen (incl. Depreciation rules) but not other admin areas. | High | Security | Manual (UAT)
UI-23 | Identity & Access Management | Roles & Permissions | Standard IT Asset roles present | Signed in with the right role; sample data loaded. | Admin › Roles & Permissions. | IT Asset Admin, IT Asset Manager, Asset Auditor, Finance (Assets), Asset Viewer exist with the access shown on the 'IT Hub Roles & Access' sheet; Contracts, Depreciation, Physical Audit are separate modules. | Medium | Security | Manual (UAT)
UI-24 | IT Asset Management | Responsive | Mobile layout | Signed in with the right role; sample data loaded. | Open Dashboard, Registry, Scan on a phone (≈ 400 px wide). | No horizontal scroll; menu opens as overlay; tables scroll inside cards. | Medium | Usability | Manual (UAT)
UI-25 | IT Asset Management | Responsive | Dark mode | Signed in with the right role; sample data loaded. | Toggle dark mode on each asset page. | Text and pills readable; no white blocks. | Low | Usability | Manual (UAT)
UI-26 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Microsoft 365 staff sign-in | Signed in with the right role; sample data loaded. | Portal › Sign in with Microsoft (staff account registered in IT Hub with a role). | Entra MFA prompt; lands in IT Hub with the access of their IT Hub role. | High | Security | Manual (UAT)
UI-27 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Partner sign-in with OTP | Signed in with the right role; sample data loaded. | Portal password + email/SMS OTP for an external partner role. | Lands in IT Hub after OTP; no second MFA in IT Hub. | High | Security | Manual (UAT)
UI-28 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Session ended message | Signed in with the right role; sample data loaded. | Disable the user in the Portal (or remove their IT Hub roles) while they are on a page; click anything. | Redirected to login with 'Your session has ended'. | High | Security | Manual (UAT)
UI-29 | Identity & Access Management | Central Identity (Ashika Portal SSO) | Session expiry (8 h) | Signed in with the right role; sample data loaded. | Stay signed in beyond the Portal token lifetime. | Asked to sign in again. | Medium | Security | Manual (UAT)
UI-30 | IT Asset Management | Performance | Large register | Signed in with the right role; sample data loaded. | Upload 2,000+ assets; open Registry, Dashboard, Depreciation. | Pages load within 3 seconds. | Medium | Performance | Manual (UAT)
MAN-FIN-01 | IT Asset Management | Finance Controls | Approval email reaches recipients | Signed in with the right role; sample data loaded. | Admin › Archive & Notifications › set recipients for 'Finance change approvals' › raise a rule change | Email with request no., change list and 'Approve in Depreciation › Approvals' | High | Positive | Manual (UAT)
MAN-FIN-02 | IT Asset Management | Finance Controls | Journal imports into Tally | Signed in with the right role; sample data loaded. | Export last month's journal › import the 'Journal (Tally)' sheet into Tally (or ERP) test company | Voucher imports; ledgers match; Dr = Cr | High | Positive | Manual (UAT)
MAN-FIN-03 | IT Asset Management | Finance Controls | Year-close email has the frozen register | Signed in with the right role; sample data loaded. | Close a year with 'Financial year closed / reopened' recipients set | Email with Excel: Fixed Asset Register, Summary by Type, Disposals | Medium | Positive | Manual (UAT)

## IT Hub Roles & Access
How sign-in and access work
1. The Ashika Portal checks WHO the person is (Microsoft 365 or Portal password + OTP, with MFA).
2. IT Hub decides WHAT they can do — from the roles assigned in IT Hub › Admin › User Master.
3. If the person is not in IT Hub User Master (same email as the Portal), sign-in is refused.
4. If they are in IT Hub but have no role (and are not Admin), sign-in is refused.
5. If they are deactivated in IT Hub or in the Portal, or all their roles are removed, they are signed out within a minute.
6. Local password sign-in remains only for IT Hub administrators (break-glass).
7. Assets are linked to people by Employee Code from User Master; each person is tagged Internal or External.
Ashika Portal — register IT Hub (sso_apps)
client_id | it-hub
redirect_uris | https://ithub-uat.niytri.com/api/auth/central/callback
client_secret | Generated by the Portal admin; given privately to the IT Hub server admin
Portal roles | No IT Hub-specific roles needed in the Portal; access is mapped in IT Hub
IT Hub roles (created by db/10_asset_roles.sql — tick them under 'Access roles' in Admin › User Master)
Role | Edit (write) | View (read only) | Use
Admin (user role = Admin) | Everything incl. Admin, Clear All Data | — | IT head / application admin
IT Asset Admin | Every IT Asset screen incl. Depreciation rules | — | Owner of the IT Asset module (no access to other admin areas)
IT Asset Manager | Asset Registry, Handovers, Contracts & AMC, Licenses, Vendors, Physical Audit | Asset Dashboard, Depreciation | Runs the asset desk
Asset Auditor | Physical Audit | Asset Dashboard, Asset Registry | Physical verification team
Finance (Assets) | Depreciation | Asset Dashboard, Asset Registry, Contracts & AMC | Fixed-asset register, AMC spend
Asset Viewer | — | Asset Dashboard, Asset Registry | Management / auditors (read-only)
Screen ↔ module key (for custom roles in Admin › Roles & Permissions)
Module key | IT Hub screen | View allows | Edit allows
assets | Asset Dashboard | Dashboard | —
asset_registry | Asset Registry, QR stickers, asset history | View assets, coverage, history | Add / edit / upload / lifecycle, finance upload, comments
asset_allocations | Handovers, Employee Assets | View handovers | Issue, bulk issue, return, record acknowledgement
asset_contracts | Contracts, AMC & Warranty | View contracts and warranty coverage | Create / edit / renew / delete contracts, covered assets
asset_depreciation | Depreciation | View register and schedules | Change depreciation rules
asset_licenses | Software Licenses & Compliance | View licenses and compliance | Add / edit licenses, assign and revoke seats
asset_vendors | Vendors | View vendors | Add / edit / delete vendors
asset_audits | Physical Audit | View audits and reports | Plan, start, scan, complete, cancel audits
Every employee can always open My Assets and acknowledge their own handovers; no role needed beyond being able to sign in.